## EDR Scenarios
User Story | Scenario_ID | Testcase_ID | Test case Descriptions | Action | Profile type | Steps | Expected Result | Assignee | Target date | Completed date | Test data | Status | Defect ID | Created Date/Time | Activation Date/Time | Updated Date/Time | Output EDR | RBM Output
CHG-9522 | SIT_SC_001 | SIT_TC_001 | Create a "Basic" subscriber without call barring,anonymous calls | Create | Basic(Public) | 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Select Subscriber Type dropdown as "public" 4)Disable self care rights-uncheck 5)Fill the mandatory details like First Name,Last Name,Email,Number,Extension 6)Admistrator- "uncheck" 7)Caller Line Identification-Own number(disable/default) 8)Block anonymous calls inbound calls -uncheck 9)Call baring - No Call baring 10)PIN for overidding call baring -disable(default PIN) 11)Language of Voicemail announcements-Dutch | Basic subscriber should be created without call barring,anonymous calls | Vignesh/Rohit | 2018-06-12 | 2018-06-12 |  | Passed
CHG-9522 | SIT_SC_002 | SIT_TC_002 | Create a "Basic" subscriber with call barring,anonymous calls | Create | Basic(Public) | 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Select Subscriber Type dropdown as "public" 4)Disable self care rights-uncheck 5)Fill the mandatory details like First Name,Last Name,Email,Number,Extension 6)Administrator- "checkin" 7)Caller Line Identification-Own number(disable/default) 8)Block anonymous calls inbound calls -checkin 9)Call baring- Baring for Premium Numbers(090x,18xy) 10)PIN for overidding call baring -disable 11)Language of Voicemail announcements-English | Basic subscriber should be created with call barring,anonymous calls | Vignesh/Rohit | 2018-06-12 | 2018-06-12 |  | Passed
CHG-9522 | SIT_SC_003 | SIT_TC_003 | Create a "Basic" subscriber by enable the disabling self care rights | Create | Basic(Public) | 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Select Subscriber Type dropdown as "public" 4)Disable self care rights-checkin 5)Fill the mandatory details like Name,Number,Extension 6)Caller Line Identification-Own number(disable/default) 7)Block anonymous calls inbound calls -check 8)Call baring -Baring for Premium Numbers(090x,18xy) and International destinations(00) 9)PIN for overidding call baring -Disable 10)Language of Voicemail announcements-German | Basic subscriber should be created with disabling self care rights | Vignesh/Rohit | 2018-06-12 | 2018-06-12 |  | Passed
CHG-9522 | SIT_SC_004 | SIT_TC_004 | Create a "Basic" subscriber with call barring,anonymous calls | Create | Basic(Public) | 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Select Subscriber Type dropdown as "public" 4)Disable self care rights-uncheck 5)Fill the mandatory details like First Name,Last Name,Email,Number,Extension 6)Administrator- "Uncheck" 7)Caller Line Identification-Own number(disable/default) 8)Block anonymous calls inbound calls -checkin 9)Call baring- Baring for International Destination(00) 10)PIN for overidding call baring -disable 11)Language of Voicemail announcements-Spanish | Basic subscriber should be created with call barring,anonymous calls | Vignesh/Rohit | 2018-06-12 | 2018-06-12 |  | Passed
CHG-9522 | SIT_SC_005 | SIT_TC_005 | Create a "Advanced" subscriber without call barring,anonymous calls | Create | Advanced(Employee) | 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Select Subscriber Type dropdown as "Employee" 4)Disable self care rights-uncheck 5)Fill the mandatory details like First Name,Last Name,Email,Number,Extension 6)Call Liner Identification -Own Number 6)Administrator field should be "uncheck" 7)Block anonymous calls inbound calls -uncheck 8)Call baring - No Call baring 9)PIN for overidding call baring -enable (any number) 11)Language of Voicemail announcements-Italian | Advance subscriber should be created without call barring,anonymous calls |  | 2018-06-12 | 2018-06-12 | 108889892 – Number used Customer Id-- 009988 | Passed
CHG-9522 | SIT_SC_006 | SIT_TC_006 | Create a "Advanced" subscriber with call barring,anonymous calls | Create | Advanced(Employee) | 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Select Subscriber Type dropdown as "Employee" 4)Disable self care rights-uncheck 5)Fill the mandatory details like First Name,Last Name,Email,Number,Extension 6)Administrator field should be "uncheck" 7)Caller Line Identification-Restricted 8)Block anonymous calls inbound calls -checkin 9)Call baring- Baring for Premium Numbers(090x,18xy) 10)PIN for overidding call baring -enable (any number) 11)Language of Voicemail announcements-Polish | Advance subscriber should be created with call barring,anonymous calls |  | 2018-06-12 | 2018-06-12 | 108889889 – Number used Customer Id-- 777777 Test data Name: Tester 2 SIT | Passed
CHG-9522 | SIT_SC_007 | SIT_TC_007 | Create a "Advanced" subscriber by enable the disabling self care rights | Create | Advanced(Employee) | 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Select Subscriber Type dropdown as "Employee" 4)Disable self care rights-checkin 5)Fill the mandatory details like Name,Number,Extension 6)Caller Line Identification-any subscribers 7)Block anonymous calls inbound calls -check 8)Call baring -Baring for Premium Numbers(090x,18xy) and International destinations(00) 9)PIN for overidding call baring -enable (any number) 10)Language of Voicemail announcements-Romanian | Advance subscriber should be created with disabling self care rights |  | 2018-06-12 | 2018-06-12 | 108889892 – Number used Customer Id-- 009988 Test data Name: Yealink T48 OTT | Passed
CHG-9522 | SIT_SC_008 | SIT_TC_008 | Create Hunt group profile with Serial Ringing for basic subscriber | Create | Basic(Public) | 1)Login to CSS portal 2)Click on Hunt Group Menu ->Create Hunt group 3)Fill the mandatory details like Name,Number,Extension 4)Select the Hunting Policy* dropdown as "Serial Ringing" 5)Time out (sec)-3 6)Language of Voicemail announcements-Dutch 7)Add a time slot by selecting Use On -Monday 8)In voicemail-Enable attach,delete 9)In No answer setting-select Destination type as Voicemail 10)Select the subscribers(basic) for that group in RHS of the page | Hunt group should be created for Basic subscribers with serial ringing | Under clarification |  |  |  | NA
CHG-9522 | SIT_SC_009 | SIT_TC_009 | Create Hunt group profile with parallel Ringing for basic subscriber | Create | Basic(Public) | 1)Login to CSS portal 2)Click on Hunt Group Menu ->Create Hunt group 3)Fill the mandatory details like Name,Number,Extension 4)Select the Hunting Policy* dropdown as "Parallel Ringing" 5)Time out (sec)-3 6)Language of Voicemail announcements-Roman 7)In voicemail-disable- attach,delete 8)In No answer setting-select Destination type as Number and give the number 10)Select the subscribers(basic) for that group in RHS of the page | Hunt group should be created for Basic subscribers with parallel ringing | Under clarification |  |  |  | NA
CHG-9522 | SIT_SC_010 | SIT_TC_010 | Create Hunt group profile with Random for advance subscriber | Create | Advanced(Employee) | 1)Login to CSS portal 2)Click on Hunt Group Menu ->Create Hunt group 3)Fill the mandatory details like Name,Number,Extension 4)Select the Hunting Policy* dropdown as "Random" 5)Time out (sec)-4 6)Language of Voicemail announcements-English 7)Add a time slot by selecting Use On -thursday 8)In voicemail-disable- attach,delete 9)In No answer setting-select Destination type as Voicemail 10)Select the subscribers(advanced) for that group in RHS of the page | Hunt group should be created for advance subscribers with random | Dhivya | 2018-06-13 | 2018-06-13 | Dhivya Hunt Group | Failed | BU-762
CHG-9522 | SIT_SC_011 | SIT_TC_011 | Create Hunt group profile with Circular for advance subscriber | Create | Advanced(Employee) | 1)Login to CSS portal 2)Click on Hunt Group Menu ->Create Hunt group 3)Fill the mandatory details like Name,Number,Extension 4)Select the Hunting Policy* dropdown as "Circular" 5)Time out (sec)-5 6)Language of Voicemail announcements-German 7)In voicemail-disable- attach,delete 8)In No answer setting-select Destination type as Number and give the number 10)Select the subscribers(advanced) for that group in RHS of the page | Hunt group should be created for advance subscribers with circular |  | 2018-06-12 | 2018-06-12 | 208549930– Number used Customer Id-- 777777 Test data Name: Tester 3 SIT | Passed
CHG-9522 | SIT_SC_012 | SIT_TC_012 | Update Basic subscriber profile to advanced | Update | Basic to advance(public to employee) | "Pre-req: Subscriber with basic profile and Hunt group(SC-2) 1)Login to CSS portal 2)Click on Subscriber Menu 3)Click on a particular subscriber with Public Profile 4)Change the Subscriber type to Employee(Change profile after 2 days of public profile created) and click on Save | Basic subscriber profile should be updated to advance profile | Under clarification |  |  |  | NA
CHG-9522 | SIT_SC_013 | SIT_TC_013 | Cease group profile for basic subscriber | delete | Basic(public) | "Pre-req: Subscriber with basic profile and Hunt group updated to Advance(SC_12) 1)Login to CSS portal 2)Click on Hunt Group Menu 3)Click on cancel symbol at the end of created Hunt group details row(after 4 days) for deleting the group | Hunt group of Basic subscriber should be ceased | Under clarification |  |  |  | NA
CHG-9522 | SIT_SC_014 | SIT_TC_014 | Cease group profile for advanced subscriber | delete | advanced(Employee) | "Pre-req: Subscriber with updated advanced profile and Hunt group (SC_12) 1)Login to CSS portal 2)Click on Hunt Group Menu 3)Click on cancel symbol at the end of created Hunt group details row(after 4 days) for deleting the group | Hunt group of advanced subscriber should be ceased | Susmithra | 2018-06-13 | 2018-06-14 |  | Passed
CHG-9522 | SIT_SC_015 | SIT_TC_015 | Update Advanced subscriber profile to basic profile | Update | advanced(Employee) to basic(public ) | Pre-req: Subscriber with Advance profile(SC_6) 1)Login to CSS portal 2)Click on Subscriber Menu 3)Click on a particular subscriber with Employee Profile 4)Change the Subscriber profile to Public -(after 5 days of the Employee profile creation) 5)Click on Conference Room Menu 6)Click on Create Conference Room(on same day ) 7)Fill the mandatory details like Name,Number,Extension,PIN and save the details 8)After some time Click on cancel symbol at the end of created conference room (on same day) for deleting the conference room | Advanced subscriber profile should be updated to basic subscriber profile and conference room should be created and deleted for same profile |  | 2018-06-13 |  | 108889889 – Number used Customer Id-- 777777 Test data Name: Tester 2 SIT | Inprogress
CHG-9522 | SIT_SC_016 | SIT_TC_016 | Cease advance subscriber profile | delete | advanced(Employee) | Pre-req: Subscriber with Advance profile(SC_12) 1)Login to CSS portal 2)Click on Subscriber Menu 3)Click on cancel symbol at the end of updated advance profile subscriber | Advance profile subscriber should be ceased | Susmithra | 2018-06-13 | 2018-06-14 |  | Passed
CHG-9522 | SIT_SC_017 | SIT_TC_017 | Activate basic subscriber profile for ceased advance subscriber(with same Number) | Create | Basic(public) | Pre-req: Subscriber with Advance profile(SC_16) 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Create a subscriber with Basic Profile with same number of that advanced profile(Next day of advance profile ceased) | Basic profile subscriber with same number of advance subscriber | Rohit | 2018-06-13 | 2018-06-13 |  | Passed
CHG-9522 | SIT_SC_018 | SIT_TC_018 | Create Hunt Group for updated basic subscriber profile | Create | Basic(public) | Pre-req: Subscriber with basic profile-(with same number of ceased advance profile)(SC_17) 1)Login to CSS portal 2)Click on Hunt Group Menu ->Create Hunt group(after 5 days of basic profile) 3)Fill the mandatory details like Name,Number,Extension 4)Select the Hunting Policy* dropdown as "Serial Ringing" 5)Time out (sec)-3 6)Language of Voicemail announcements-Dutch 7)Add a time slot by selecting Use On -Monday 8)In voicemail-Enable attach,delete 9)In No answer setting-select Destination type as Voicemail 10)Select the subscribers(basic) for that group in RHS of the page | Hunt group should be created for updated basic subscriber profile | Vignesh |  |  |  | NA
CHG-9522 | SIT_SC_019 | SIT_TC_019 | Cease Hunt Group for updated basic subscriber profile | delete | Basic(public) | Pre-req: Subscriber with basic profile-(with same number of ceased advance profile)(SC_18) 1)Login to CSS portal 2)Click on Hunt Group Menu 3)Click on cancel symbol at the end of created Hunt group details row(after 2 days OF Hunt group creation) for deleting the group | Hunt group should be deleted for updated basic subscriber profile | Vignesh |  |  |  | NA
CHG-9522 | SIT_SC_020 | SIT_TC_020 | Cease basic profile against backdate and create advance subscriber profile | delete | Basic(public) | Pre-req-Subscriber with Basic profile(SC_17) 1)Login to CSS portal 2)Click on Subscriber Menu 3)Select particular subscriber with basic profile and delete that subscriber before the bill date(after 27 days based on date created) 4)Click on Subscriber Menu 5)Create a subscriber with Advanced Profile (with ceased basic subscriber number) | Basic profile should be deleted and advance subscriber profile should be created | Rohit | 2018-06-13 | 2018-06-13 |  | Passed
CHG-9522 | SIT_SC_021 | SIT_TC_021 | Activate already existing profile | create | advanced(employee) | Pre-req-Subscriber with advanced profile(SC_20) 1)Login to CSS portal 2)Click on Subscriber Menu->Create Subscriber 3)Create a subscriber with advanced Profile with same number of that advanced profile in pre-req(on Next day of advance profile ceased) 4)It should throw some error | Error message: EDR will be errored out stating that the profile is already active for the subscriber. Ideally RBM shouldn't receive such records. | Rohit | 2018-06-13 |  |  | Inprogress
CHG-9522 | SIT_SC_022 | SIT_TC_022 | Create huntgroup profile on future date | create | advanced(employee) | Pre-req-Subscriber with advanced profile(SC_20) 1)Login to CSS portal 2)Click on Hunt Group Menu ->Create Hunt group(after month of advance profile created) 3)Fill the mandatory details like Name,Number,Extension 4)Select the Hunting Policy* dropdown as "Serial Ringing" 5)Time out (sec)-3 6)Language of Voicemail announcements-Dutch 7)Add a time slot by selecting Use On -Monday 8)In voicemail-Enable attach,delete 9)In No answer setting-select Destination type as Voicemail 10)Select the subscribers(advanced) for that group in RHS of the page | Hunt group should be created | Vignesh | 2018-06-13 |  |  | Passed
CHG-9522 | SIT_SC_023 | SIT_TC_023 | Update subscriber profile with same type | Update | Advance to advance | Pre-req-Subscriber with Advance profile 1)Login to CSS portal 2)Click on Subscriber Menu 3)Edit the subscriber type and select "employee" again for same profile and click on save | Error message: EDR will be errored out stating that the profile is already active for the subscriber. Ideally RBM shouldn't receive such records. |  | 2018-06-13 |  | 108889899– Number used Customer Id—009989 | Inprogress
CHG-9522 | SIT_SC_024 | SIT_TC_024 | Update Huntgroup Profile | Update | advanced(employee) | Pre-req-Subscriber with Advance profile & Hunt group 1)Login to CSS portal 2)Click on Subscriber Menu 3)select the subscriber with Advance profile & Hunt group 4)Edit the Hunt group subscribers with basic subscriber and click on save | Error message: EDR will be errored out stating that the profile is already active for the subscriber. Ideally RBM shouldn't receive such records. |  | 2018-06-13 |  | 108889899– Number used Customer Id—009989 | Inprogress
CHG-9522 | SIT_SC_025 | SIT_TC_025 | Update profile to group | Update | Advanced to Conference Room | Pre-req-Subscriber with Advance profile & Hunt group 1)Login to CSS portal 2)Click on Subscriber Menu 3)select the subscriber with Advance profile & Hunt group 4)Edit the subscriber advance profile to conference room | Error message: EDR will be errored out stating that the profile is already active for the subscriber. Ideally RBM shouldn't receive such records. |  | 2018-06-13 |  | 108889889 – Number used Customer Id-- 777777 Test data Name: Tester 2 SIT | Inprogress
CHG-9522 | SIT_SC_026 | SIT_TC_026 | Activate one more profile on existing profile | Update | advanced(employee) | Pre-req-Subscriber with Advance profile & Hunt group 1)Login to CSS portal 2)Click on Subscriber Menu 3)select the subscriber with Advance profile & Hunt group 4)Create one more basic profile for same subscriber with same details | EDR will be errored out since a subscriber can have only one profile active at a time. Ideally RBM shouldn't receive such records | Rohit | 2018-06-14 | 2018-06-14 |  | Inprogress
CHG-9522 | SIT_SC_027 | SIT_TC_027 | Create fax number for basic subscriber and send the fax | Create | Basic(public) | 1)Login to CSS portal 2)Click on FAX menu 3)Click on create fax number 4)Fill the mandatory details like Name,Email destination for incoming faxes,Number,Extension 5)Select the subscribers for this feature in RHS of the page 5)Enable Receive a copy of outgoing faxes,Receive reports of outgoing and incoming faxes and click on save 6)Click on send fax tab 7)Fill the details likeFax number,destination number,page header,page content,file upload 8)click on send button 9)Verify Fax log | Fax number should be created for basic subscriber and fax should be able to send |  | 2018-06-14 |  | 0108889896 -- Number Used Name: Cisco kabelweg OTT | Inprogress
CHG-9522 | SIT_SC_028 | SIT_TC_028 | Create fax number for advance subscriber and send the fax | Create | advanced(employee) | 1)Login to CSS portal 2)Click on FAX menu 3)Click on create fax number 4)Fill the mandatory details like Name,Email destination for incoming faxes,Number,Extension 5)Select the subscribers for this feature in RHS of the page 5)Enable Receive a copy of outgoing faxes,Receive reports of outgoing and incoming faxes and click on save 6)Click on send fax tab 7)Fill the details likeFax number,destination number,page header,page content,file upload 8)click on send button 9)Verify Fax log | Fax number should be created for advance subscriber and fax should be able to send |  | 2018-06-14 |  | 0108889892 --Number Used Name: Justine Baibe | Inprogress
CHG-9522 | SIT_SC_029 | SIT_TC_029 | Voicemail for personal profile and group | Update | Voicemail | 1)Login to CSS portal 2)Click on Voicemail menu 3)Select the voicemail group option and show options and click on "Change" button | Voicemail details should be dispalyed |  | 2018-06-13 | 2018-06-13 | 020777777 --Number Used SIT Tester 1 | Passed
CHG-9522 | SIT_SC_030 | SIT_TC_030 | Create a device for basic subscriber | Create | Basic(public) | 1)Login to CSS portal 2)Click on device menu 3)Click on "Create device" 4)Fill the details like Name,Brand,Model and MAC address and click on next 5)Map the device with basic subscriber | Device should be created and mapped for basic subscriber | Rohit | 2018-06-14 |  |  | Passed
CHG-9522 | SIT_SC_031 | SIT_TC_031 | Create a device for advanced subscriber | Create | advanced(employee) | 1)Login to CSS portal 2)Click on device menu 3)Click on "Create device" 4)Fill the details like Name,Brand,Model and MAC address and click on next 5)Map the device with advance subscriber | Device should be created and mapped for advance subscriber | Vignesh | 2018-06-13 |  |  | Passed
CHG-9522 | SIT_SC_032 | SIT_TC_032 | Default forward | Update | Default Forward | 1)Login to CSS portal 2)Select any number from the dropdown in "Forward all numbers not in use to"-subscribers number,group number and click on "save" | default number for forward should be selected | Vignesh | 2018-06-13 |  |  | Passed
CHG-9523 | SIT_SC_033 | SIT_TC_033 | Create a hunt group and conference room for basic subscriber | Create | Basic(public) | 1)Login to CSS portal 2)Click on Hunt Group Menu ->Create Hunt group 3)Fill the mandatory details like Name,Number,Extension 5)Click on Conference Room Menu 6)Click on Create Conference Room(on same day ) 7)Fill the mandatory details like Name,Number,Extension,PIN and save the details | Basic subscriber with both Hunt group and conference room should not be created | Vignesh | 2018-06-14 | 2018-06-14 |  | Passed
CHG-9524 | SIT_SC_034 | SIT_TC_034 | Create a hunt group and conference room for advanced subscriber | Create | advanced(employee) | 1)Login to CSS portal 2)Click on Hunt Group Menu ->Create Hunt group 3)Fill the mandatory details like Name,Number,Extension 5)Click on Conference Room Menu 6)Click on Create Conference Room(on same day ) 7)Fill the mandatory details like Name,Number,Extension,PIN and save the details | Advance subscriber with both Hunt group and conference room should not be created | Vignesh | 2018-06-14 | 2018-06-14 |  | Passed
CHG-9525 | SIT_SC_035 | SIT_TC_035 | Enabling call forward options for customer/Subscriber admin |  | Call Forward | 1)Login to CSS portal 2)click on Seeting option and move to call forward tab 3)For Unconditional: Not active,select destination type as "number"and enter the number 4)For Call forward active during add the timeslot for any of the day 5)For Busy: voicemail select the destination type as "voicemail" 6)For Call forward active during-select the Timeslot and enable 7)For Unavailable: voicemail - select the destination type as "voicemail" 8)Timeout: voicemail-elect destination type as "number"and enter the number 9)Click on save button | Call Forward should be enabled | Susmithra | 2018-06-14 | 2018-06-14 |  | Passed
CHG-9526 | SIT_SC_036 | SIT_TC_036 | Enabling Voicemail/Speeddial options for customer/Subscriber admin |  | Voicemail/Sppeddial | 1)Login to CSS portal 2)click on Seeting option and move to Voicemail tab 3)Enter the email address and enable the attach ,delete field 4)Click on save button 5)Move to speed dials tab and click on "add" option 6)Select the option from the dropdown and destination number and click on save button | Voicemail/Speeddial should be enabled | Susmithra | 2018-06-14 | 2018-06-14 |  | Passed

## CDR Regression scenarios
User Story | Type | Scenario_ID | Testcase_ID | Test Case Description | Steps | Expected Result | Assignee | Target Date | Completion date | Status | Defect ID | Type of Usage made | Source Number | Destination Number | Forwarded To | CLI Number | Date | Time | Call duration (mm:ss) | Status | Pass/Fail | Defect ID | Comments
CHG-9522 | Simulatin of calls | SIT_SC_037 | SIT_TC_037 | Verify that the simulation of calls made for Intra HPBX Basic Calls is working fine and validation of invoice is sucessful | Line to Line - Intra customer calls Dial local (CLIP) Dial local with CLIR Enter the source number Enter the Destination Number Enter the duration to make a call Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. |  | 2018-06-14 |  |  |  | Intra HPBX Basic calls | 5352000 5352000 | 5352003 5352000 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_038 | SIT_TC_038 | Verify that the simulation of calls made for Inter HPBX Basic Calls is working fine and validation of invoice is successful | Line to Line - Inter customer group Dial local (CLIP) Dial full E164 (CLIP) Enter the source number Enter the Destination Number Enter the duration to make a call Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. |  | 2018-06-14 |  |  |  | Inter HPBX Basic calls | 8889897 108889897 | 8889899 108889899 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_039 | SIT_TC_039 | Verify that the simulation of calls made for Offnet calls to/from HPBX is working fine and validation of invoice is successful | Offnet calls to/from HPBX HPBX customer to NL residential - Dial E164 (CLIP) HPBX customer to NL residential - Dial E164 (CLIR) NL residential to HPBX customer - Dial E164 (CLIP) NL residential to HPBX customer - Dial E164 (CLIR) Enter the source number Enter the Destination Number Enter the duration to make a call Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. |  | 2018-06-14 |  |  |  | Offnet HPBX Basic calls | 108889899 108889899 208549943 208549943 | 208549943 208549943 365352000 108889899 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_040 | SIT_TC_040 | Verify that the simulation of calls made for International HPBX Basic calls is working fine and validation of invoice is successful | International HPBX Basic calls HPBX NL to HPBX IE - Dial E164 HPBX IE to HPBX NL - Dial E164 HPBX NL to hiQ IE - Dial E164 hiQ IE to HPBX NL- Dial E164 Enter the source number Enter the Destination Number Enter the duration to make a call Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. |  | 2018-06-14 |  |  |  | International HPBX Basic calls | 108889898 35312456497 108889898 35312456497 | 353214347800 108889892 353899875075 108889892 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_041 | SIT_TC_041 | Verify that the simulation of calls made for Special Basic Call[special number] is working fine and validation of invoice is successful | Different CLI selected for intra customer Different CLI selected for international (NL residential) Enter the source number Enter the Destination Number Enter the duration to make a call Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. |  | 2018-06-14 |  |  |  | Special Basic Call | 2000 108889898 | 2002 31619732344 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_042 | SIT_TC_042 | Verify that the simulation of calls made for Call forward Unconditinal is working fine and validation of invoice is successful | Inter PBX - CFB to number national CFB to NL residential Enter the source number Enter the Destination Number Enter the duration to make a call Enter the call forwarded number so that the call will be forwarded automatically Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Call Forward Unconditional | 365352000 365352000 | 365352002 365352002 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_043 | SIT_TC_043 | Verify that the simulation of calls made for Call Forward Busy is working fine and validation of invoice is successful | Intra PBX - CFT to extension Inter PBX - CFT to number national Enter the source number Enter the Destination Number Enter the duration to make a call Enter the call forwarded number so that the call will be forwarded automatically Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Call Forward Busy | 2000 365352002 | 2002 108889898 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_044 | SIT_TC_044 | Verify that the simulation of calls made for Call Forward Timeout is working fine and validation of invoice is successful | CFT to NL residential CFT to VM Enter the source number Enter the Destination Number Enter the duration to make a call Enter the call forwarded number so that the call will be forwarded automatically Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Call Forward Timeout | 2002 365352000 | 2000 365352000 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_045 | SIT_TC_045 | Verify that the simulation of calls made for Call Forward Unavailable is working fine and validation of invoice is successful | Intra PBX - CFNA to extension Inter PBX - CFNA to number national Enter the source number Enter the Destination Number Enter the duration to make a call Enter the call forwarded number so that the call will be forwarded automatically Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Call Forward Unavailable | 2002 108889898 | 2004 2004 | 2000 2002 | Yes
CHG-9522 | Simulatin of calls | SIT_SC_046 | SIT_TC_046 | Verify that the simulation of calls made for No barring (Blacklist) is working fine and validation of invoice is successful | user is allowed to make phone call to Ziggo customer care nr user is allowed to make phone call to extension nr Enter the source number Enter the Destination Number Enter the duration to make a call Barring should not be invoked Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | No barring (Blacklist) | 365352000 2000 | 9001884 2004 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_047 | SIT_TC_047 | Verify that the simulation of calls made for Barring for Premium numbers is working fine and validation of invoice is successful | user is allowed to make phone call to Ziggo customer care nr phone call to premium nr (0900 x xx xx) Enter the source number Enter the Destination Number Enter the duration to make a call Barring should be invoked Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Barring for Premium numbers (090x, 18xy) (Blacklist) | 365352002 365352002 | 09001884 90012345 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_048 | SIT_TC_048 | Verify that the simulation of calls made for Barring for Premium numbers (090x, 18xy) and international destinations is working fine and validation of invoice is successful | user is allowed to make phone call to Ziggo customer care nr phone call to premium nr (0900 x xx xx) Enter the source number Enter the Destination Number Enter the duration to make a call Barring should be invoked Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Barring for Premium numbers (090x, 18xy) and international destinations (00) (Blacklist) | 365352002 365352002 | 09001884 900156789 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_049 | SIT_TC_049 | Verify that the simulation of calls made for Suspension (Whitelist) is working fine and validation of invoice is successful | user is allowed to make phone call to Ziggo customer care nr user is allowed to make phone call to international nr Enter the source number Enter the Destination Number Enter the duration to make a call Barring should be invoked// suspenion should be applicable as this is suspended for particulay perios Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Suspension (Whitelist) | 365352002 365352002 | 9001884 2003 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_050 | SIT_TC_050 | Verify that the simulation of calls made for Call Forward Blocking (Blacklist) is working fine and validation of invoice is successful | user is allowed to make phone call to Ziggo customer care nr user is allowed to make phone call to extension nr Enter the source number Enter the Destination Number Enter the duration to make a call Call forward should be blocked as it is blacklisted Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Call Forward Blocking (Blacklist) | 365352002 108889892 | 108889892 2002 FW2003 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_051 | SIT_TC_051 | Verify that the simulation of calls made for Toll free number is working fine and validation of invoice is successful | Different CLI selected for intra customer Different CLI selected for international (NL residential) Enter the source number Enter the Destination Number Enter the duration to make a call Give the inputs to Device team to perform simulation of calls Validate CDR Output file format and the invoice generated | Output for CDR File should be validated sucessfully. Verify that the charges for the calls made is accurate in invoice sucessfully. | [5 empty] | Toll free number | 2000 108889898 | 2002 31619732344 |  | Yes
CHG-9522 | Simulatin of calls | SIT_SC_052 | SIT_TC_052 | Verify that the deactivated customer after suspension can make calls and the service should be restricted. | After Making the suspension Enter the source number Enter the Destination Number Enter the duration to make a call Give the inputs to Device team to perform simulation of calls It should not allow the customer to make a call as the service is deactivated. | Output for CDR File should be validated sucessfully. Verify that the charges for the calls should not be present as it is restricted | [5 empty] | Deactivated customer | It should be blocked | It should be blocked
Defect | Simulatin of calls | SIT_SC_053 | SIT_TC_053 | Verify the the rounding off logic of the calls made is working fine | • For O_DURATION it should be rounded off correctly • For O_EVENT_DTM runding off logic should be verifed correctly Convert I_START_TIME to the format YYYY/MM/DD-hh-mm-ss.tt by rounding and assign it to EL_CALL_A_TIME_RBM. EL_DURATION_HNRD_SEC = I_DURATION * 100 and then rounded. | Rounding off logic should be verified successfully for the calls made | [5 empty] | Internationa and Local Calls |  |  |  | Yes

## E2E Validation
User Story | Type | Scenario_ID | Testcase_ID | Test Case Description | Steps | Expected Result | Test data | Status | Defect ID | Comments
CHG-9522 | E2E Validation | SIT_SC_054 | SIT_SC_054 | Verify that New order should be sent to Tracy sucessfully and the service Id allocated in SIPWISE wth prefix as SIPEU for the below combination of products: Zakelijk Internet Pro Zakelijk Hosted Bellen[HPBX] | • Create lead and converts into opportunity. • Add Zakelijk Internet Pro(Small) in basket page • Complete configuration for the Zakelijk Internet Pro(Small) • Click Installation information per site and give the technical contact, wish date details • Click Assign billing and fill the details and save • Click to upload product basket • Create quote and send quote for approval in opportunity page • Move to Ready for order state in salesforce • Check if outgoing xml have the changetypecode(401) and Contractcardcode with below values,Zakelijk Internet Pro - 1 • Process the order in Tracy • Tracy work order flow • 1.Aanmaken • --->import SFDC • ---->Click the CSV file • ----->open the File---check the Name and save the file in Local Disc. • 2.MSD • -->Gegevens importen • -->Browse file(select) • -->volgende • -->Instellingen voor • -->semicolon • -->Volgende • -->Salesforce date Importane • -->Volgende • -->Volgende • -->Indienen • -->voltoolen • *Refresh MSD an check 3files will be updated wait for the 1st field to be all in 111 stage. • 3.Tracy • --->Click the check box • --->select verwerken tr@cy order • --->Select SFDC file and click(above) • ---->open the file • ----->Note the case ID • 4.Werkscherm • *Credit check • #Find the Case id and click • !! Toevegen • *Geen voorwaarden---Opslaan---Opslaan-->ja • *Controlle contract DTV • #Search by case id • !! Akkord--->Opslaan--->Ok-->jaa • *Order • #Intake werkorder • ! Toon alle regio's • *Search by case id • # ok-->Selct the caseid--->muturen cp interface(Reflected as green)It wont go for change point. • # Select the case id --Ok • *Relatie • -->Project heder(Stefan zikkener) • *aanvarg • -->today date • Akkord--->Opslaan--->ok--->jaa • #Bevesting PL • !Toon alle regio's • *select case id-->Muturen cpe • *Akkord--opslaan-->ok--->jaa • #Leevoren order • !Toon alle regio's • *select the case id • #contract • ! click the number • *Service ID(PTSID214563) PTSID214562 should be changed to SIPEUXXXXXX for for Pan EU • *Today Date-->opslaan • *color will be changed to yeelow to white do it for all the products. • akkord--->opslaan. • #controle Tc order • !Select the number • *Akkord--Opslaan • *Facturing • #facturing • !Toon Bulk sfdc • *click the case id--select • #Debiter number(click)--Select the number • Not save--ok • !Toon bulk Sfdc • *select the case id • !Automatich facturien--ok • # inevoer RBM • ! Toon bulk Sfdc • *select the Case id • #akkoord--opsllan..--ok--jaa • ! Toon bulk sfdc • *select the case id.CLick the check box • !Automatich facturien--ok • 5.Muturen Case status #realtie !change to 3000 --opslaan • Upload and process file in MSD • Get the case id in tracy • Check EDR Flow form SIPWISE platform to Mediation successfully • Check and process the order till 3000 • Check if the order get process from DWH • Check whether order status become "Active" • Check Invoice generation is successful in RBM and validate the Charges accordingly | • Service ID PTSID214562 should be changed to SIPEUXXXXXX for Pan EU successfully • Check the invoice generation at RBM and validate the charges accordingly
CHG-9522 | E2E Validation | SIT_SC_055 | SIT_SC_055 | Verify that add order should be sent to Tracy sucessfully and the service Id allocated in SIPWISE wth prefix as SIPEU for the below combination of products: Zakelijk Internet Pro Zakelijk Hosted Bellen[HPBX] Zakelijk TV | • Create lead and converts into opportunity. • Add Zakelijk Internet Pro(Small) in basket page • Complete configuration for the Zakelijk Internet Pro(Small) • Click Installation information per site and give the technical contact, wish date details • Click Assign billing and fill the details and save • Click to upload product basket • Create quote and send quote for approval in opportunity page • Move to Ready for order state in salesforce • Check if outgoing xml have the changetypecode(401) and Contractcardcode with below values,Zakelijk Internet Pro - 1 • Process the order in Tracy • Tracy work order flow • 1.Aanmaken • --->import SFDC • ---->Click the CSV file • ----->open the File---check the Name and save the file in Local Disc. • 2.MSD • -->Gegevens importen • -->Browse file(select) • -->volgende • -->Instellingen voor • -->semicolon • -->Volgende • -->Salesforce date Importane • -->Volgende • -->Volgende • -->Indienen • -->voltoolen • *Refresh MSD an check 3files will be updated wait for the 1st field to be all in 111 stage. • 3.Tracy • --->Click the check box • --->select verwerken tr@cy order • --->Select SFDC file and click(above) • ---->open the file • ----->Note the case ID • 4.Werkscherm • *Credit check • #Find the Case id and click • !! Toevegen • *Geen voorwaarden---Opslaan---Opslaan-->ja • *Controlle contract DTV • #Search by case id • !! Akkord--->Opslaan--->Ok-->jaa • *Order • #Intake werkorder • ! Toon alle regio's • *Search by case id • # ok-->Selct the caseid--->muturen cp interface(Reflected as green)It wont go for change point. • # Select the case id --Ok • *Relatie • -->Project heder(Stefan zikkener) • *aanvarg • -->today date • Akkord--->Opslaan--->ok--->jaa • #Bevesting PL • !Toon alle regio's • *select case id-->Muturen cpe • *Akkord--opslaan-->ok--->jaa • #Leevoren order • !Toon alle regio's • *select the case id • #contract • ! click the number • *Service ID(PTSID214563) PTSID214562 should be changed to SIPEUXXXXXX for for Pan EU • *Today Date-->opslaan • *color will be changed to yeelow to white do it for all the products. • akkord--->opslaan. • #controle Tc order • !Select the number • *Akkord--Opslaan • *Facturing • #facturing • !Toon Bulk sfdc • *click the case id--select • #Debiter number(click)--Select the number • Not save--ok • !Toon bulk Sfdc • *select the case id • !Automatich facturien--ok • # inevoer RBM • ! Toon bulk Sfdc • *select the Case id • #akkoord--opsllan..--ok--jaa • ! Toon bulk sfdc • *select the case id.CLick the check box • !Automatich facturien--ok • 5.Muturen Case status #realtie !change to 3000 --opslaan • Upload and process file in MSD • Get the case id in tracy • Check EDR Flow form SIPWISE platform to Mediation successfully • Check and process the order till 3000 • Check if the order get process from DWH • Check whether order status become "Active" • Check Invoice generation is successful in RBM and validate the Charges accordingly | • Service ID PTSID214562 should be changed to SIPEUXXXXXX for Pan EU successfully • Check the invoice generation at RBM and validate the charges accordingly
CHG-9522 | E2E Validation | SIT_SC_056 | SIT_SC_056 | Verify that Change order should be sent to Tracy sucessfully and the service Id allocated in SIPWISE wth prefix as SIPEU for the below combination of products: Zakelijk Internet Pro Zakelijk Hosted Bellen[HPBX] | • Create lead and converts into opportunity. • Add Zakelijk Internet Pro(Small) in basket page • Complete configuration for the Zakelijk Internet Pro(Small) • Click Installation information per site and give the technical contact, wish date details • Click Assign billing and fill the details and save • Click to upload product basket • Create quote and send quote for approval in opportunity page • Move to Ready for order state in salesforce • Check if outgoing xml have the changetypecode(401) and Contractcardcode with below values,Zakelijk Internet Pro - 1 • Process the order in Tracy • Tracy work order flow • 1.Aanmaken • --->import SFDC • ---->Click the CSV file • ----->open the File---check the Name and save the file in Local Disc. • 2.MSD • -->Gegevens importen • -->Browse file(select) • -->volgende • -->Instellingen voor • -->semicolon • -->Volgende • -->Salesforce date Importane • -->Volgende • -->Volgende • -->Indienen • -->voltoolen • *Refresh MSD an check 3files will be updated wait for the 1st field to be all in 111 stage. • 3.Tracy • --->Click the check box • --->select verwerken tr@cy order • --->Select SFDC file and click(above) • ---->open the file • ----->Note the case ID • 4.Werkscherm • *Credit check • #Find the Case id and click • !! Toevegen • *Geen voorwaarden---Opslaan---Opslaan-->ja • *Controlle contract DTV • #Search by case id • !! Akkord--->Opslaan--->Ok-->jaa • *Order • #Intake werkorder • ! Toon alle regio's • *Search by case id • # ok-->Selct the caseid--->muturen cp interface(Reflected as green)It wont go for change point. • # Select the case id --Ok • *Relatie • -->Project heder(Stefan zikkener) • *aanvarg • -->today date • Akkord--->Opslaan--->ok--->jaa • #Bevesting PL • !Toon alle regio's • *select case id-->Muturen cpe • *Akkord--opslaan-->ok--->jaa • #Leevoren order • !Toon alle regio's • *select the case id • #contract • ! click the number • *Service ID(PTSID214563) PTSID214562 should be changed to SIPEUXXXXXX for for Pan EU • *Today Date-->opslaan • *color will be changed to yeelow to white do it for all the products. • akkord--->opslaan. • #controle Tc order • !Select the number • *Akkord--Opslaan • *Facturing • #facturing • !Toon Bulk sfdc • *click the case id--select • #Debiter number(click)--Select the number • Not save--ok • !Toon bulk Sfdc • *select the case id • !Automatich facturien--ok • # inevoer RBM • ! Toon bulk Sfdc • *select the Case id • #akkoord--opsllan..--ok--jaa • ! Toon bulk sfdc • *select the case id.CLick the check box • !Automatich facturien--ok • 5.Muturen Case status #realtie !change to 3000 --opslaan • Upload and process file in MSD • Get the case id in tracy • Check EDR Flow form SIPWISE platform to Mediation successfully • Check and process the order till 3000 • Check if the order get process from DWH • Check whether order status become "Active" • Check Invoice generation is successful in RBM and validate the Charges accordingly | • Service ID PTSID214562 should be changed to SIPEUXXXXXX for Pan EU successfully • Check the invoice generation at RBM and validate the charges accordingly